## task-1_Damco_assign_NN
TEST CASE : DAMCO SOLUTIONS ASSIGNMENT- MANUAL
Project Name: | Damco Assignment- Task 1 |  | Reviewed by: |  |  |  | Test Data | Valid | Invalid
Module Name: | Work Place |  | Reviewed date: |  |  |  | Date | .Present Date: 06-03-2024 .Future date: 14-05-2024 | .Past date: 15-08-2000 .Invalid date: 32-13-2021
Sub Modeule: | Search Functionality |  | Approved by : |  |  |  | Floor | Numeric: (1,2,78,111, ,029) | .Negative:'-1,-2,-29 .Decimal / Zero: 2.5,17.4, 0 .String: 3rd, fifth,FLOOR6 | . Roman: VI, III, X,V . Keep Blank .Special Characters: @#%&)
Created by: | Niraj Nirala | [5 empty] | List of equipment | .Single:PC/Phone/Flip Chart Board, Projector .Multiple: PC, Phone/Flip Chart Board,PC, Phone/Flip Chart Board,PC, Phone, Projector | Equipment not selected from list
Creation date: | 2023-03-06 | [5 empty] | Smoking restrictions* | Yes, No | Rarely, Frequent,1,0 |  | *Assumption: Smoking restriction only accepting boolean expression (Yes/No)
Requirement ID | Requirement | Test Scenrio ID | Test Scenaio | TC ID | Test Case Description | Pre-requisite Conditions | Test Data | Test Steps | Expected Result | Actual Result | Priority | Complexity | Status | Defect ID | Comments*
R_01 | System shall allow user to perform search, set criteria, filter workplaces, sort, and navigate. | TS_01 | Perform search with all search criteria set | TC_01 | Verify search is working with all search criteria set | The webpage is functional | Date: 29-05-2024 Floor: 6 Equipment: Phone Smoking: Yes | Enter the value and Hit Search button | Should display workplaces matching criteria
R_02 | System shall allow searching without setting parameters. | TS_02 | Perform search without setting any search parameters | TC_02 | Verify search without setting any search parameters | The webpage is functional | With No Search Parameter | Hit Search button | Should display all available workplaces
R_03 | System shall allow searching workplaces by provided parameters. | TS_03 | Search workplaces by provided parameters: Date, Floor, Equipment, Smoking Restrictions | TC_03 | Verify workplaces by provided parameters: Date, Floor, Equipment, Smoking Restrictions | The webpage is functional | Date: 11-04-2024 Floor: 8 Equipment: Projector Smoking: No | Enter the value and Hit Search button | Should display workplaces matching criteria
R_04 | System shall allow searching only for date range that is not in the past. | TS_04 | Attempt to search for past dates | TC_04 | Verify to search for past dates | The webpage is functional | Date: 31-10-2018 | Enter the value and Hit Search button | Should display toast error message in "Can't search past dates"
R_05 | System shall allow sorting search results by all available fields. | TS_05 | Sort search results by all available fields in (ascending and descending) | TC_05 | Verify Sort search results by (A) Ascending Order (B) Descending Order 1.Date 2.Floor 3.Equipments 4.Smoking Restrictions | The webpage is functional | 1. Date: Ascending 2. Date:Descending 3. Floor: Ascending 4. Floor:Descending 5. Equipment: Ascending 6. Equipment :Descending 7. Smoking Restrictions: Ascending 8. Smoking Restrictions:Descending | Sort the result | Should Display results sorted by Date, Floor, Equipments, Smoking Restrictions in ascending/descending order
R_06 | System shall validate provided data before search. | TS_06 | Check invalid data in search fields and attempt to search | TC_06 | Verify invalid data in search fields and attempt to search | The webpage is functional | 1. Date: 31-22-2025 2. Floor: '5thFloor' 3. Equipment: 'Music System' 4. Smoking: 'Rarely' | Enter the value and Hit Search button | Should display appropriate toast error messages for invalid data
R_07 | System shall provide search results without delay. | TS_07 | Perform search and verify results are displayed without delay | TC_07 | Verify search and verify results are displayed without delay | The webpage is functional | Need to Search with valid parameters and observe time taken (verify response time) | Enter the value and Hit Search button | Should display search results promptly
R_08 | System shall provide flexible navigation between results. | TS_08 | Navigate between search results using pagination or similar | TC_08 | Verify navigation between search results using pagination | The webpage is functional | Search with multiple pages of results | Check various navigations pages | should able to navigate between search result pages
R_09 | System shall provide a user friendly interface. | TS_09 | Verify the interface is user-friendly with clear labels and intuitive design | TC_09 | Verify the interface is user-friendly with clear labels and intuitive design | The webpage is functional | Observe the search interface, its should have good look & feel, frequest usable buttons/navigations are easly discoverable | Observe the Interface | Interface has clear labels and userfriendly design, look and feel
R_10 | Search result table shall be read only. | TS_10 | Attempt to edit or modify data in the search result table | TC_10 | Verify edit or modify data in the search result table | The webpage is functional | Check edit data in the search result table | Try to edit or modify search result | Data in search result tables should be read-only
NOTE: The number of test cases can be increased by applying conditions separately and test data separately, here mapped only to the requirements to save time and avoid lenthiness.
Bad Requirements Identifications: | Requirement 2: "System shall allow searching without setting search parameters. What would "searching without parameters" mean? Better to define a default search to avoid any confusion.
Requirement 6: "System shall validate provided data before search". It should specify what kind of validation is expected. What happens if invalid data is provided?
Requirement 4: "System shall allow searching only for the date range that is not in the past." It should specify the exact behavior for future dates and how past dates should be handled.
Requirement 7: "System shall provide search results without delay." What is considered "without delay"? It should define a specific response time.
Requirement 9: "System shall provide user-friendly interface" lacks specifics. Define usability criteria
Requirement 10: "Search result table shall be read only." Is it read-only for all users? Only certain roles? It should specify the conditions for read-only access.
Total No. TS
Total No. TC
Total No. TCs Pass
Total No. TCs Fail
Total No. TCs Deffered

## task-2_Estimation_WBS
ESTIMATE WITH WORK BREAKDOWN STRUCTURE (WBS) FOR TEST ACTIVITIES
PROJECT TITLE | Damco Assignment- Task 2 |  |  | COMPANY NAME |  | Damco
PROJECT MANAGER | - |  |  | DATE |  | 2024-03-06
PROJECT | PROJECT TITLE: DAMCO ASSIGNMENT -TASK 2
PHASE | Requirement Analysis | Test Data Preparation |  | Test Case Design |  | Test Environment Setup |  | Test Execution |  | Defect Reporting and Tracking |  | Test Summary & Documentation | (H)
ROUGH ESTIMATE (WEEK) | 2 Weeks | 1 Week |  | 2 Weeks |  | 1 Weeks |  | 3 Weeks |  | 1 Week |  | 1 Week
ESTIMATED EFFORT (HOUR) |  | 9 Hours | (H) | 14 Hours | (H) | 10 Hours | (H) | 20 Hours | (H) | 08 Hours | (H) | 10 Hours
TASK
| Understand customer needs and system requirements | Prepare Test Data for Search Functionality | 3 | Test Case Design for Search Functionality | 4 | Set up a production-like environment for testing |  | Execute Test Cases for Search Functionality | 5 | Report Defects Found During Testing | 5 | Test Summary Report | 5
|  | Prepare Test Data for Sorting Functionality | 2 | Test Case Design for Sorting Functionality | 4 |  |  | Execute Test Cases for Sorting Functionality | 4 | Update Test Cases Based on Test Results | 3 | Test Completion Report | 3
|  | Prepare Test Data for Invalid Input | 2 | Test Case Design for Validation of Data | 4 |  |  | Execute Test Cases for Data Validation | 5 |  |  | Updated Test Cases | 2
|  | Prepare Test Data for Interface Navigation | 2 | Test Case Design for Navigation and Interface | 2 |  |  | Execute Test Cases for Navigation and Interface | 6
RESULTS: (Customer gets) | 1. The customer will receive thoroughly tested search functionality
2. Customers will gain confidence in the usability and accuracy of the system
3. Documentation of the detailed test will be provided to the customer
4. A high level of quality with minimal defects impacting critical functions will be delivered to the customer
ASSUMPTIONS: | 1. Testing environment is available and set up.
2. Access to all necessary test data.
3. Developers are available for bug fixes and retesting.
4. Testers have necessary skills and training for executing test cases.
5. User stories provided cover the main functionalities.
HIGH LEVEL DESCRIPTIONS: | 1. The estimated test activities include detailed test case design, test data preparation, test execution, defect reporting, and test summary/documentation.
2. Each activity contributes to ensuring thorough testing coverage and quality assurance for the workplace search functionality.
3. The customer can expect a set of well-documented test cases, comprehensive test data sets, detailed test execution reports, and a final test summary report with findings and recommendations.
4. This approach aims to deliver an efficient and effective testing process, focusing on meeting the specified requirements and ensuring a user-friendly and reliable search feature for the application.
5. Test data will be prepared to cover different scenarios, including valid and invalid inputs. Execution of test cases will ensure proper functionality, and any defects found will be reported and tracked.
DELIVERABLES: | 1. Test Cases
| 1.1 | Test Cases for searching with different criteria
| 1.2 | Test Cases for sorting search results
| 1.3 | Test Cases for validating input data before search
| 1.4 | Test Cases for navigating search results and interface
2. Test Data Sets
| 2.1 | Test Data for different date ranges, floors, equipment, and smoking restrictions
| 2.2 | Test Data for sorting search results
| 2.3 | Test Data for invalid input scenarios
| 2.4 | Test Data for navigating between search results and interface
3. Test Execution Reports
| 3.1 | Execution Report for searching
| 3.2 | Execution Report for sorting search results
| 3.3 | Execution Report for validating input data before search
| 3.4 | Execution Report for navigating search results and interface
4. Defect Reports and Updated Test Cases
| 4.1 | Defect Reports
| 4.2 | Updated Test Cases
5. Test Summary Report, Test Completion Report, Updated Test Cases

## task-2_UStory_task_estimation
USER STORY AND TASK ESTIMATION
User Story/Task ID | DESCRIPTIONS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | Comment (if any)
# User Registration (Feature 1)
1. User Story | As a user, I want to register into the system so that I can view working places I have booked. | 14 Hours
Task 1 | 1. Design test cases for user registration flow.
Task 2 | 2. Prepare test data for valid and invalid registration scenarios.
Task 3 | 3. Execute tests on registration process and data validation.
Task 4 | 4. Report and track any registration-related defects.
# Booking of Office Place (Feature 2)
2. User Story | As a user, I want to book available working places for the future so that nobody could take the place. | 10 Hours
Task 1 | 1. Create test cases for booking process including future dates and availability checks.
Task 2 | 2. Generate test data for booking scenarios.
Task 3 | 3. Execute tests on booking feature and cancellation functionality.
Task 4 | 4. Report and track any issues with booking or cancellation.
# User Roles (Feature 3-A):
3. User Story | As a user, I want to have the ability to cancel booking so that another user could book it instead. | 8 Hours
Task 1 | 1. Design test cases for user cancellation process
Task 2 | 2. Prepare test data for cancellation scenarios.
Task 3 | 3. Execute tests on cancellation functionality.
Task 4 | 4. Report and track any issues with booking cancellation.
# User Roles - Office Manager (Feature 3B):
4. User Story | As an office manager, I want to manage working places so that the system provides valid up-to-date information to system users. | 8 Hours
Task 1 | 1. Design test cases for office manager functionality (add, edit, delete workplaces)
Task 2 | 2. Prepare test data for managing workplaces.
Task 3 | 3. Execute tests on managing workplaces and data accuracy.
Task 4 | 4. Report and track any issues with managing workplace information.
# Native Mobile Application (Feature 4):
5. User Story | As a user, I want to use the mobile application for system usage so that I can do it any time. | 6 Hours
Task 1 | 1. Create test cases for mobile app functionality (registration, booking, user roles)
Task 2 | 2. Generate test data for mobile app scenarios.
Task 3 | 3. Execute tests on mobile app features and usability.
Task 4 | 4. Report and track any issues with mobile app integration and functionality.
TOTAL |  | 46 Hours | 0 | 0 | 0 | 0 | 0 | 0
Expected Results for the Customer: | 1. Detailed test cases covering all user stories and new features.
2. Comprehensive test data sets for various scenarios (registration, booking, user roles).
3. Execution of tests ensuring the reliability and usability of the new features.
4. Identification and documentation of any defects for resolution.
5. Test summary report providing an overview of test coverage, results, and recommendations for improvements.
Overall Approach: | 1. The estimated activities aim to ensure thorough testing of the new increment's features.
2. Focus on user stories to create relevant test cases and test data.
3. Execution of tests to validate the functionality, usability, and performance.
4. Timely reporting and tracking of any issues found during testing.
5. Delivery of a comprehensive test summary report for review and feedback.

## task-3_test_coverage
TASK-3: COMPLEX REPORTING (Based on Assumptioned made)
1. Test Coverage Report:
Requirement | Test Cases | Status | Remarks
System shall allow users to perform search, set criteria, filter, sort, and navigate results. | TC_01, TC_02, TC_03 | Passed | NA
System shall allow searching without setting parameters. | TC_02 | Passed | NA
System shall allow searching workplaces by provided parameters. | TC_03 | Passed | NA
System shall allow searching only for the date range that is not in the past. | TC_04 | Passed | NA
System shall allow sorting search results by all available fields. | TC_05 | Passed | NA
System shall validate provided data before search. | TC_06 | Passed | NA
System shall provide search results without delay. | TC_07 | Failed | NA
System shall provide flexible navigation between results. | TC_08 | Passed | NA
System shall provide user-friendly interface. | TC_09 | Passed | NA
Search result table shall be read-only. | TC_10 | Passed | NA
2. Test Execution Summary:
Description | Number |  | Remarks
Total Test Cases Executed: | 10 |  | NA
Passed: | 9 |  | NA
Failed: | 1 |  | NA
Blocked: | 0 |  | NA
Not Executed: | 0 |  | NA
3. Defect Summary:
Defect ID | Description | Severity | Status
DEF_01 | Unable to sort results by 'Equipment' field. | High | Open
DEF_02 | UI is not responsive on mobile devices. | Medium | In Review
DEF_03 | Incorrect validation message on date input. | Low | Closed
4. Recommendations: | 1. Resolve DEF_01 to ensure sorting functionality works as expected.
2. Fix DEF_02 to improve user experience on mobile devices.
3. Verify DEF_03 fix and update validation messages for clarity.
4. Need to add additional test cases for edge cases and boundary conditions.
5. Test Completion Summary: | 1. All test cases for requirements were executed.
2. Identified defects are being tracked and resolved.
3. Test coverage is comprehensive, ensuring functionality is thoroughly tested.
4. Report includes detailed results, allowing easy understanding by stakeholders.
5. Recommended improvements will enhance the overall quality of the application.
Structured Report with Status
Task 1 - Requirements Analysis and Coverage: |  | Status | Remarks
· Overview of the web-form and requirements. |  | Done
· Test data proposed with reasons. |  | Done
· Test cases outlined with coverage of each requirement. |  | Done
· Identified bad requirements with suggestions for improvement. |  | Done
Task 2 - Estimation:
· Detailed Work Breakdown Structure (WBS). |  | Done
· Estimated timeframes for each activity. |  | Done
· Assumptions made during estimation. |  | Done
· Expected deliverables and quality level. |  | Done
Overall Conclusion:
· Summary of tasks performed. |  | Done
· Challenges faced and how they were addressed. |  | Done
· Recommendations for improving testing processes. |  | Done
· Projected outcomes based on the test plan. |  | Done
Additional:
This structured report aims to provide a comprehensive overview of the tasks performed, the approach taken, and the expected outcomes. It ensures clarity for the Project Manager or Test Lead reviewing the report, minimizing the need for additional questions.